## Slide 1: DNP Initiative ENG-003 Standard Design Process Overview Configuration Management Benchmarking Group June 12, 2017

## Slide 2: DNP Initiative ENG-003 Overview
Vision:
Implement a standard plant modification process to promote efficient use of engineering resources and streamlined engineering changes.
  Simplified design process common to all stations
  Industry-wide training applicability
  Standardized process software
  Facilitate sharing of information between stations

## Slide 3: DNP Initiative ENG-003 Overview
What has been accomplished over the past year?
16 Member Steering Committee
  Developed SDP procedure IP-ENG-001
    SME table top review
    4 Utilities piloted the SDP procedure
  Conducted SDP workshops and webcasts
  Conducted SDP training for Utility SMEs
  Developed Change Management Plan
  Developed Standard Qualification
  Developed and deployed a Nantel SDP Training Module
Notes: Development of SDP Procedure IP-ENG-001 (Mar – June 2016)
Table Top Review (June 2016)
  Conducted with 14 subject matter experts
    Pilot plant representatives
    Engineering vendors
Pilot Process (Oct – Jan 2016)
  McGuire, Surry, Sequoyah, Vogtle
  Validate procedure, training, change management plans
  Comments incorporated prior to Rev 0 issue

## Slide 4: DNP Initiative ENG-003 Overview
What other SDP activities are in progress?
  Currently developing standard SDP software
    Electronic preparation, review and approval
    Tool to manage Engineering Changes during development through implementation and closure
  Industry Item Equivalency Working Group
  Industry Digital Design Working Group

## Slide 5: DNP Initiative ENG-003 Overview
Major Milestones:
IP-ENG-001, Standard Design Process, Rev 0 issued
Efficiency Bulletin for DNP Initiative ENG-003 as been issued
  Process – July 28, 2017
  Software – July 2018
Design Oversight Working Group established
Nuclear Community Website

## Slide 6: DNP Initiative ENG-003 Overview
Governance of IP-ENG-001:
Industry owned and maintained procedure
  Design Oversight Working Group (DOWG)
    Similar structure and charter as ERWG
    Executive Oversight Committee
    Engineering VP/Director Peer Group
DOWG Charter
    Focus Areas
      Monitor industry engineering change performance
      Procedure and Software updates

## Slide 7: DNP Initiative ENG-003 Overview
Simplified & Streamlined Processes:
Engineering Change Types: screening drives to lowest complexity while maintaining safety & reliability
  Design Change - “Cafeteria-Style” graded approach
  Design Equivalent Change
  Commercial Change
Other Elements
  Design Attribute Review Tool
  Temporary Modifications
  Emphasis on Teamwork / Stakeholder engagement

## Slide 8: SDP Procedure Overview
IP-ENG-001 Format
  Purpose, Scope, Applicability
  Definitions
  Roles and Responsibilities
  Procedure
  References
  Utility Interfaces
  Attachments
Flowchart – Procedure
Utility Interface Procedure

## Slide 9: SDP Procedure Overview
SDP Flowchart Attachment 2 (11x17 Handout)
Six Phases:
  Initial Scoping Phase
  Conceptual/Common Design Phase
  Detailed Design Phase
  Planning Phase
  Installation/Testing Phase
  Design Closure Phase
Notes: 11x17 handout to follow along.
The procedure uses a flowchart style to step through the process. This convention is modeled after the EPRI Guideline (1008254) and INPO (AP-929) documents, but modified to provide more guidance for each step. These basic rules were created to keep the procedure more visual to reduce the amount of explanation needed. There will be times where the procedure will jump to other attachments and other procedures and we will discuss these as we go through the training. It will probably not fit your utility writer’s guide.
Attachment 1 of the SDP has further explanation of the flowcharting conventions.
Blue, dotted lined boxes contain steps to be performed using existing utility procedures and are optional if the utility procedure allows
Black, solid lined boxes contain steps to be performed using IP-ENG-001
Blocks are numbered based on overall process phase number followed by the step number
Solid line arrows are steps to typically be performed, dotted line arrows may be used if beneficial or at management discretion
Steps are to be performed in order, unless noted

## Slide 10: SDP Procedure Overview Flowcharting Conventions
Start or End of a
process
Off page
reference
to additional
steps
Document to be
issued
Decision to
determine
path
Ref
point
Step Number
Responsible Owner
Description of step
Blue, dotted line means
Performed by utility procedure

## Slide 11: SDP Procedure Overview
Utility Interface Procedures:
Endorse the use of IP-ENG-001
Utilities will implement IP-ENG-001 as written
Delineate transitions to IP-ENG-001
Do not redefine, reinterpret, or modify the intent of
  IP-ENG-001
Provides the “Rosetta Stone” and “road map” to Utility terminology and procedures

## Slide 12: SDP Procedure Overview Initial Scoping Phase
Request Change
Plant Health Process
Determine Change Type
Advanced Work Authorization?
Initial Scoping Study (if needed)

## Slide 13: SDP Procedure Overview Conceptual/Common Design Phase
Implement at Multiple Sites?
Develop Bounding Design Inputs
Conceptual Impact Review Meeting
Reviews
Complete Conceptual Design
Kickoff and Team Formation
Yes – Common Design
No – Normal Change Type Form

## Slide 14: SDP Procedure Overview Detailed Design Phase
Develop Detailed Design Package - as Determined by Change Type
Determine Test Requirements and Acceptance Criteria (if applicable)
Reviews
Approve / Issue Change Package
Document Special Implementation Instructions
Final Impact Review Meeting (if needed)

## Slide 15: SDP Procedure Overview Planning Phase
Plan Work Implementation Package
Schedule Work Orders
Installation
Testing
Removal (If Temporary)

## Slide 16: SDP Procedure Overview Installation/Testing Phase
Implement Change
Turnover to Operations/Return to Service
Removal of Temp Change (If Applicable)
Perform Tests
Turnover to Operations/Return to Service (If Applicable)
Field Change Requests (If Needed)

## Slide 17: SDP Procedure Overview Design Closure Phase
Updates to Reflect As-Built Configuration
Closeout Engineering Change

## Slide 18: SDP Overview
Questions?