## Slide 1: New Nuclear Lessons Learned Breakout
TVA Representative & KEPCO E&C with participants from Westinghouse, GVH, Bruce Power, and Others

## Slide 2: Labeling Consistency
IEEE 805-1984 Energy Industry Identification System (EIIS), is being used to present a common language of communication that will permit a user to correlate a system, structure, or component with that of another organization for the purposes of reporting, comparison, or general communication.
Implementing experience is finding challenges in alignment between individual owner labeling practices.

## Slide 3: BIM & IT Software Integration Strategy (Construction vs. Operations)
Construction Phase Alignment: The core focus during construction is aligning the 3D/4D BIM modeling, project management, and procurement software between the NSSS Vendor (GEH, Westinghouse) and the EPC contractor to maintain seamless data consistency.
Operational Phase Customization: Post-construction, customization is inevitable because each utility/customer operates different legacy IT systems for enterprise asset management (EAM) and maintenance.
Data Conversion as a Solution: Rather than attempting a single, overly complex end-to-end IT platform (which previously failed in legacy US projects like VC Summer), modern best practice focuses on robust Data Conversion/Translation from construction BIM into operational management systems.

## Slide 4: Korean Fleet Model: Repeatability & Troubleshooting Feedback System
Institutional Continuity: Korea’s nuclear ecosystem is structured around a single owner/utility (KHNP) and a single primary engineering firm (KEPCO E&C), enabling decades of continuous data retention and design software evolution.
Fleet Repeatability & The Troubleshooting Bucket:
  The APR1400 fleet (Shin-Kori Units 3/4 & 5/6, Shin-Hanul Units 3/4, and Barakah Units 1–4) has evolved through continuous, iterative deployment.
  Non-critical design flaws or field interferences (e.g., minor piping/C&I clashes) are systematically stored in a "Troubleshooting Database/Bucket." Because KEPCO E&C retains engineering continuity, these lessons are guaranteed to be resolved in subsequent project designs.
  Vendors like GE-Hitachi and Westinghouse intend to follow the Korean Fleet Model by constantly feed lessons learned from lead deployment units (e.g., Vogtle 3&4, Darlington Unit 1) back into the "Standard Design" baseline for subsequent unit deployment.
Owner-Driven Construction Management:
  Even when construction contractors (e.g., Hyundai, Samsung) change through competitive bidding, KHNP retains 100% of the schedule, cost, and Work Package data. This allows the owner to enforce realistic schedule reductions (e.g., cutting 5+ months) on subsequent builds.
  Bruce Power experienced similar execution and cost improvements as experienced by the Korean Fleet during their sequenced plant refurbishment projects. Bruce only realized this when they took on PM control internally like the Korean model.

## Slide 5: Lead Unit Lessons Learned & Construction Schedule Overlap
While waiting 5 years for a lead unit’s operational feedback before building Unit 2 is ideal, it is financially and operationally unfeasible due to supply chain, workforce, and capital costs. Consequently, utilities implement real-time iteration, incorporating lessons during ongoing construction/commissioning.
The primary failure mode of legacy US builds was commencing physical site construction prior to completing and thoroughly vetting the design. TVA and SMR developers now enforce a strict "Hold" on site construction until design confidence is fully established.

## Slide 6: Configuration Management (CM) Challenges & BIM Instance Branching
Fragmentation Across Jurisdictions: Deploying a single standard reactor design across different countries or utilities (e.g., TVA in the US, OPG in Canada, European/Polish standards) creates CM challenges due to varying national regulations, labeling, and documentation standards.
Project Space / Instance Branching: To handle these variations without corrupting the core standard design, engineering teams establish separate, independent BIM/CM project instances (branches) for each customer/site.
Automated 3D-to-2D Extraction (KEPCO E&C Benchmark): KEPCO E&C builds a unified 3D BIM model (using Bentley tools) and utilizes an in-house automated program to extract 2D Isometric drawings and paper documentation required for site construction, ensuring seamless 3D-2D synchronization.

## Slide 7: Evolution Toward True "Digital Twin"
3D BIM vs. True Digital Twin:
  3D BIM: Focuses on spatial geometry, clash detection, and automated material quantity takeoff (MTO) linked to procurement.
  Digital Twin: A comprehensive, real-time integrated platform combining 3D geometry with exact installed component serial numbers, Work Order completion status, revision history, live operating data, and full plant simulator integration.
As-Built Laser Scanning (KHNP Success Case): To bridge the gap between initial BIM designs and actual physical field installations, KHNP executes full-scope 3D Laser Scanning post-construction (e.g., Shin-Kori 3/4 & 5/6). This laser-mapped data updates the BIM model into a 100% accurate, physical As-Built "Digital Twin" prior to operational handover.

## Slide 8: KEY TAKEAWAYS FOR EXECUTIVE SUMMARY
Seamless Handover is Essential: Construction BIM models and operational management tools serve different purposes; a structured Data Conversion pipeline is critical for smooth utility handover.
Owner-Led Data Retention and Construction Management Drives Fleet Savings: Long-term retention of Work Package data and Troubleshooting Databases by the Owner/Lead Engineer is the single most effective driver for reducing cost and construction schedules across a reactor fleet.
Laser Scanning Realizes True Digital Twins: Combining 3D BIM models with post-construction 3D Laser Scanning creates an exact physical As-Built Digital Twin, providing unmatched efficiency for long-term plant operations and maintenance.