Change

Facility

Configuration

Information

(FCI)

?

CM

EQUILIBRIUM

CM001

EVALUATE IDENTIFIED PROBLEM OR DESIRED CHANGE

Change

Physical

Configuration

?

CHANGE

DESIGN

REQUIREMENTS

?

DO

NOTHING MORE

NO

No

No

YES

Yes

Yes

CM002

DESIGN REQUIREMENTS CHANGE

PROCESS

CM003

PHYSICAL CONFIGURATION CHANGE AUTHORIZATION PROCESSES

CM004

FACILITY

CONFIGURATION

INFORMATION (FCI) CHANGE

PROCESS

### CM Equilibrium Restoration Diagram

# Assumptions

- CM is understood to include all plant personnel and processes – not just Engineering

- These PIs are independent of any specific utility/plant process or resource base

- Measurement techniques/methods probably don’t exist for some indicators at this time

- The CM Conformance Restoration Diagram is adopted and used by NEI and INPO

- All CM problems/discrepancies are reported on CRs

- Either CR cause or event codes and their assignments allow binning and tracking of CM-related information or someone familiar with CM will need to evaluate them for the period.

# Definitions/Notes

- Configuration Management (CM) – An integrated management program that assures:

- governing requirements are identified and satisfied in the physical configuration and the facility configuration information, and

- the physical configuration matches the facility configuration information.

- In addition to CM self-assessments performed by Engineering or CM, other departments and process checks should be considered. For example, Operations clearance tag audits, Chemistry sampling, audits of Temporary Modification times, etc.  Problems found during these assessments would be reported on CRs.

- CRs = Condition Reports, commonly used problem reporting mechanism. Some facilities call them Problem Reports (PRs), Problem Evaluation Reports (PERs), etc. CRs may cover the gamut of configuration problems, from an oil leak in someone’s car in the plant parking lot to a pump’s failure to meet rated output to an unexpected flux change in the core. It may also be appropriate to record and monitor the number of “repeat” occurrences of CRs by category. It would also be advisable to identify “legacy” issues so as not to distort the significance of current problems. Facilities are encouraged to review their existing event-coding scheme to determine if they can be used effectively to evaluate CM issues.

- Change Requests are typically a uniform requesting mechanism to get items into a review cycle for scoping, validity determination, action assignment, etc. Some facilities call them Action Requests (ARs), Engineering Change Requests (ECRs), Engineering Service Orders (ESOs), etc.

- Cumulative effects of pending or temporary changes to the design basis calculations, e.g., piping stress calcs, heat load calcs, service water heat load calcs, containment heat load calcs, electrical load calcs, etc. should be considered as a leading indicator to potential design requirement problems. Tracking of incremental changes is advised so that individual changes that do not erode design/safety margin will not collectively present a problem.

- FCRs = Field Change Requests, mechanism for identifying in-process changes for Physical Configuration changes after authorization was received. The term could also apply to Physical Configuration package revisions. Avoidable FCRs and Physical Configuration package revisions are those that should not have occurred with adequate prior planning or design development. Tracking the number, percentage and age of FCRs and/or Physical Configuration package changes may be an informative measure.

- Physical Configuration changes include items/processes in addition to traditional modifications or engineering changes. For example, Physical Configuration changes apply to Operations valve and equipment line-ups, chemistry changes, computer hardware/software changes, nuclear fuel/core changes, etc.

- Facility Configuration Information needs to include documents/databases outside of engineering. For example, Operations/Chemistry/Maintenance procedures or training materials that include structure, system, or component design/license basis information.

- CM001, CM002, etc. correspond to the core process designators in the NEI Standard Nuclear Performance Model.

## Process:	CM Equilibrium

Examples:	CM Culture
Recognizing & Managing return to Equilibrium

Roll-up of issues identified in other Areas

A

| Indicator Name: | Overall CM Program Effectiveness |
| --- | --- |
| Definition: | Composite score for CM-related leading and lagging indicators |
| Reason for Reporting: | 1. To Advise Management (Problems, ways to Improve) 2. 10CFR Requirements for Safety-Related items 3. Minimize/Avoid Cost of Recovery when equilibrium is upset 4. Check/Adjust Program |
| Calculations: | How indicator is arrived at: - For leading indicators – develop customer survey - For lagging indicators – composite of results from CM001-004 |
| Reporting Frequency | 1. For leading indicators - annually 2. For lagging indicators - monthly |
| INPO OEO Reference | 4c |
| Comments | Goal would be to show a positive trend over a period of time Results can be displayed using a red, green, yellow, white color scheme |

B

| Indicator Name: | CM Awareness and Training |
| --- | --- |
| Definition: | # of CRs or other plant indicators indicating in-adequacies in CM awareness or training |
| Reason for Reporting: | 1. People need to understand process to ensure success 2. Improve Human Performance |
| Calculations: | How indicator is arrived at: Review of CRs or other indicators (either all, % sample or CR database word search)) |
| Reporting Frequency | Monthly |
| INPO OEO Reference | 2f, 2i, 3a, 3l |
| Comments | See Assumptions 5 & 6 Goal would be to show positive trend |

C

| Indicator Name: | CM Self-Assessment |
| --- | --- |
| Definition: | # of CRs written as result of CM self assessments |
| Reason for Reporting: | Identify/Prioritize and Propose Corrective Actions for Improvements |
| Calculations: | How indicator is arrived at: Review of CRs (either all, % sample or CR database word search) |
| Reporting Frequency | Monthly |
| INPO OEO Reference | 1k, 1j |
| Comments | Include all functional areas, i.e., Ops tagging audit, Temp Mod audit, etc. It may be appropriate to distinguish between internal self-assessments versus external driven assessments/audits/inspections. See Definition 2 |

Process:	CM001 – Evaluate Identified Problem Or Desired Change

Examples:	Problems identified by CRs such as:

- Documents  Physical Plant

- Ops Lineup  Procedure

- Equipment Out-of-Tolerance

Desired Changes such as:

- Modification/Temp Mod Change Request

- Tech Spec / Procedure Change

- Equivalency

- Abandon-In-Place

- Red Tag Components

- Storage Requirements

- Scaffolding Request

A

| Indicator Name: | Effectiveness of Identification Process for CM Related CRs |
| --- | --- |
| Definition: | 1. # and % of CM-related CRs to total CRs per period 2. # and % of CM-related CRs considered valid |
| Reason for Reporting: | Effectiveness of process in identifying CM Problems for Improvement |
| Calculations: | How indicator is arrived at: Review of CRs (either all, % sample or CR database word search) |
| Reporting Frequency | Monthly |
| INPO OEO Reference | 1a, 4c |
| Comments | See Assumptions 5 & 6 and Definition 3 & 4 |

B

| Indicator Name: | Timeliness of Identification for CM Related CRs |
| --- | --- |
| Definition: | 1. Time from initiation of CR to assignment of action to resolve 2. # of open CM related CRs 3. Time from initiation of change request to assignment of action to resolve 4. # of open CM related Desired Changes |
| Reason for Reporting: | Reduce Risk Exposure for CM Related Issues – How Long Out of Equilibrium |
| Calculations: | How indicator is arrived at: Review of CRs (either all, % sample or CR database word search) |
| Reporting Frequency | Monthly |
| INPO OEO Reference | 1d, 2i |
| Comments | See Assumptions 5 & 6 and Definition 3 & 4 |

C

| Indicator Name: | Cost Performance for Evaluation Process |
| --- | --- |
| Definition: | Work-hours to evaluate CM-related CRs |
| Reason for Reporting: | 1. Identify Process Improvements 2. Effective Use of Resources |
| Calculations: | How indicator is arrived at: From data extracted from facility time keeping records |
| Reporting Frequency | Monthly for internal use, may be averaged for annual reporting |
| INPO OEO Reference | N/A |
| Comments | Excludes work-hours to develop changes indicated in CM002, 3 & 4 |

Process:	CM002 - Design Requirements Change Process

#### Examples:	Problems identified by CR Process

- SAR/ Tech Spec Changes

- Calculation / Design Basis / Specification Changes

- Setpoint changes

- New / Revised Requirements

Desired Changes such as:

- Power Uprate

- Steam Generator Replacement

- Condenser Retubing

A

| Indicator Name: | Effectiveness of Design Requirement Change Process |
| --- | --- |
| Definition: | # of CRs written specifically against Design Requirements change process |
| Reason for Reporting: | Potential for CM Problems (Process is not working properly.) |
| Calculations: | How indicator is arrived at: Review of CRs (either all, % sample or CR database word search) |
| Reporting Frequency | Monthly |
| INPO OEO Reference | 1a, 4d, 4e, 4f, 4l |
| Comments |  |

B

| Indicator Name: | Timeliness of Design Requirements Change Process |
| --- | --- |
| Definition: | 1. Time from assignment of action as a Design Requirement change to closure 2. # of outstanding changes in Design Requirements Change process |
| Reason for Reporting: | 1. To reduce Risk Exposure 2. Improve Performance: Effective use of Resources |
| Calculations: | How indicator is arrived at: From work tracking system, from initiation to closeout (excludes regulator time) |
| Reporting Frequency | Monthly |
| INPO OEO Reference | 4k |
| Comments | Average all items in process See Definition 5 |

C

| Indicator Name: | Cost Performance for Design Requirements Change Process |
| --- | --- |
| Definition: | Work-hours to process Design Requirements changes |
| Reason for Reporting: | 1. Identify Process Improvements 2. Promote Effective Use of Resources |
| Calculations: | How indicator is arrived at: From data extracted from facility time keeping records |
| Reporting Frequency | Monthly for internal use, may be averaged for annual reporting |
| INPO OEO Reference | N/A |
| Comments | Typically these hours are in the Engineering and Licensing Depts. |

Process:	CM003 - Physical Configuration Change Authorization Processes

#### Examples:	Problems identified by CR Process

- Midnight Mods

- Drawing not matching Plant

- Improper Maintenance

- Part No. / Model No. Discrepancy

- Vendor Changes (not ‘design’)

Desired Changes such as:

- Resolve Obsolescence issues

- Improvements in Reliability

- Margin Risk Reduction

- Software (process)

A

| Indicator Name: | Effectiveness of Physical Change Authorization Processes |
| --- | --- |
| Definition: | 1. # of CRs written specifically against Physical Configuration change authorization processes 2. Score on Physical Configuration Change package review 3. # of avoidable FCRs |
| Reason for Reporting: | Potential for CM Problems if Process is not working properly |
| Calculations: | How indicator is arrived at: Review of CRs (either all, % sample or CR database word search) |
| Reporting Frequency | Monthly |
| INPO OEO Reference | 4e, 4f |
| Comments | Can be subdivided by processes: Mods, Temp Mods, Facility Changes, Equivalencies, Valve / Equipment lineups, etc |

B

| Indicator Name: | Timeliness of Physical Change |
| --- | --- |
| Definition: | 1. Time from assignment of action as a Physical Configuration change to closure 2. # of outstanding changes in the Physical Config change processes |
| Reason for Reporting: | Reduce risk exposure how long you were out of equilibrium |
| Calculations: | How indicator is arrived at: From work tracking system |
| Reporting Frequency | Monthly |
| INPO OEO Reference | 2i |
| Comments |  |

C

| Indicator Name: | Cost Performance |
| --- | --- |
| Definition: | Work-hours to develop Physical Configuration Changes |
| Reason for Reporting: | 1. To Identify Potential Problems 2. Promote Effective Use of Limited Resources |
| Calculations: | How indicator is arrived at: From data extracted from facility time keeping records |
| Reporting Frequency | Monthly for internal use, may be averaged for annual reporting |
| INPO OEO Reference | N/A |
| Comments |  |

Process:	CM004 - Facility Configuration Information (FCI) Change Process

Examples:	Changes to:

- SAR

- Drawings

- Databases

- Procedures containing Configuration Information

- Vendor Tech Manuals

- Software (data)

A

| Indicator Name: | Effectiveness of Facility Configuration Information (FCI) Change Process |
| --- | --- |
| Definition: | 1. # of CRs written specifically against FCI change process 2. # of CRs written against problems or discrepancies with FCI |
| Reason for Reporting: | To identify Potential Problems in CM Program |
| Calculations: | How indicator is arrived at: Review of CRs (either all, % sample or CR database word search) |
| Reporting Frequency | Monthly |
| INPO OEO Reference | 4e |
| Comments |  |

B

| Indicator Name: | Timeliness of FCI Process |
| --- | --- |
| Definition: | 1. Time from assignment of action as a FCI change to closure 2. # of open items (or backlog) in FCI change process - # of Physical Configuration Changes completed, but paperwork still outstanding |
| Reason for Reporting: | Reduce Risk |
| Calculations: | How indicator is arrived at: From work tracking system |
| Reporting Frequency | Monthly |
| INPO OEO Reference | 4e |
| Comments |  |

C

| Indicator Name: | Cost Performance of FCI Process |
| --- | --- |
| Definition: | Work-hours to process FCI changes |
| Reason for Reporting: | 1. To identify potential problems 2. Promote the Effective Use of Limited Resources |
| Calculations: | How indicator is arrived at: From data extracted from facility time keeping records |
| Reporting Frequency | Monthly for internal use, may be averaged for annual reporting |
| INPO OEO Reference | N/A |
| Comments |  |